## Relationship Trnsfr Gannt Chart
RELATIONSHIP TRANSITION DAILY GANTT CHART
Client Relationship Transition Project | [5 empty] | John Smith | [16 empty] | 2024-01-02 |  |  |  |  | 2024-06-02
PROJECT NAME | [5 empty] | CLIENT NAME | [16 empty] | START DATE |  |  |  |  | END DATE
Task ID | Task Name | Start Date | End Date | Duration (In Days) | time axis 2024-01-02 to 2024-06-02
T01 | P&S Contract Signing | 2024-01-02 | 2024-01-02 | 1 | bar: 2024-01-02
CLIENT COMMUNICATIONS PLAN |  | 2024-01-10 | 2024-06-01 | 144 | bar: 2024-01-10 to 2024-03-24
| A. Content Development re: Merger Announcement - Seller & Buyer |  |  | 1
T02 | 1. Script and record 3 email messages with seller and buyer for distribution | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T03 | 2. Draft Facebook Announcement | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T04 | 3. Draft LinkedIn Announcement | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T05 | 4. Draft correspondence for letters/emails going to customers re: announcement | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T06 | 5. Draft Invitations to Open House #1 | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T07 | 6. Draft Invitations to Open House #2 | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T08 | 7. Draft Invitations to Retirement Party | 2024-01-03 | 2024-01-09 | 7 | bar: 2024-01-03 to 2024-01-09
T09
B. Content Distribution re: Merger Announcement - Buyer
T10 | Send Bomb Bomb Email Campaign Message 1 with seller & buyer | 2024-01-10 | 2024-01-10 | 1 | bar: 2024-01-10
T11 | Post Facebook Merger Announcement | 2024-01-10 | 2024-01-10 | 1 | bar: 2024-01-10
T12 | Post LinkedIn Merger Announcement | 2024-01-10 | 2024-01-10 | 1 | bar: 2024-01-10
T13 | Send Bomb Bomb Email Campaign Message 2 with seller & buyer | 2024-01-24 | 2024-01-24 | 1 | bar: 2024-01-24
T14 | Send Bomb Bomb Email Campaign Message 3 with seller & buyer | 2024-02-07 | 2024-02-07 | 1 | bar: 2024-02-07
T15 | Schedule catering/assign staff to support event/post/mail for Open House #1 | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T16 | Send Invitations to Open House #1 | 2024-01-15 | 2024-01-15 | 1 | bar: 2024-01-15
T17 | Host Open house event #1 | 2024-01-31 | 2024-01-31 | 1 | bar: 2024-01-31
T18 | Schedule catering/assign staff to support event/post/mail for Open House #2 | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T19 | Send Invitations to Open House #2 | 2024-02-01 | 2024-02-01 | 1 | bar: 2024-02-01
T20 | Host Open House Event #2 | 2024-02-15 | 2024-02-15 | 1 | bar: 2024-02-15
T21 | Schedule catering/assign staff to support event/post/mail for Retirement Party | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T22 | Send Invitations to Retirement Party (bring gifts!) | 2024-03-01 | 2024-03-01 | 1 | bar: 2024-03-01
T23 | Host Retirement Party | 2024-03-15 | 2024-03-15 | 1 | bar: 2024-03-15
CLIENT ONBOARDING PROCESS
A. Data Integration Project - Buyer
T24 | Assign stafff to data conversion | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T25 | Add all A Clients to Redtail Database - COMPLETE RECORDS | 2024-01-03 | 2024-01-10 | 8 | bar: 2024-01-03 to 2024-01-10
T26 | Add all B Clients to Redtail Database - COMPLETE RECORDS | 2024-01-11 | 2024-01-18 | 8 | bar: 2024-01-11 to 2024-01-18
T27 | Add all C Clients to Redtail Database - COMPLETE RECORDS | 2024-01-19 | 2024-01-26 | 8 | bar: 2024-01-19 to 2024-01-26
T28 | Add all D Clients to Redtail Database - COMPLETE RECORDS | 2024-01-27 | 2024-02-02 | 7 | bar: 2024-01-27 to 2024-02-02
T30 | Set all clients up on Weekly Market Commentary | 2024-02-05 | 2024-02-08 | 4 | bar: 2024-02-05 to 2024-02-08
T31 | Set all clients up on Opt-In Email Lists | 2024-01-03 | 2024-02-02 | 31 | bar: 2024-01-03 to 2024-02-02
T32 | Email Calendar of Events to all acquired clients | 2024-01-03 | 2024-02-02 | 31 | bar: 2024-01-03 to 2024-02-02
T33 | Deliver "Meet the Team" Contact Information | 2024-01-03 | 2024-02-02 | 31 | bar: 2024-01-03 to 2024-02-02
B. Client Personal Contact Program - Buyer and Seller
T34 | Schedule A Client Appoinments & Personal Introductions - INTRO MEETING | 2024-01-11 | 2024-01-18 | 8 | bar: 2024-01-11 to 2024-01-18
T35 | Review A Client Files and History | 2024-01-11 | 2024-01-18 | 8 | bar: 2024-01-11 to 2024-01-18
T36 | Schedule B Client Appoinments & Personal Introductions - INTRO MEETING | 2024-01-19 | 2024-01-26 | 8 | bar: 2024-01-19 to 2024-01-26
T37 | Review B Client Files and History | 2024-01-19 | 2024-01-26 | 8 | bar: 2024-01-19 to 2024-01-26
T38 | Schedule C Client Appoinments & Personal Introductions - INTRO MEETING | 2024-01-27 | 2024-02-03 | 8 | bar: 2024-01-27 to 2024-02-03
T39 | Review C Client Files and History | 2024-01-27 | 2024-02-03 | 8 | bar: 2024-01-27 to 2024-02-03
T40 | Schedule B Client Appoinments & Personal Introductions - INTRO MEETING | 2024-02-04 | 2024-02-11 | 8 | bar: 2024-02-04 to 2024-02-11
T41 | Review D Client Files and History | 2024-02-04 | 2024-02-11 | 8 | bar: 2024-02-04 to 2024-02-11
T42 | Schedule A Client - EMONEY & INVESTMENT REVIEWS | 2024-03-05 | 2024-03-12 | 8 | bar: 2024-03-05 to 2024-03-12
T43 | Schedule B Client - EMONEY & INVESTMENT REVIEWS | 2024-03-13 | 2024-03-20 | 8 | bar: 2024-03-13 to 2024-03-20
T44 | Schedule C Client - INVESTMENT REVIEWS AND RECOMMENDATIONS | 2024-03-27 | 2024-04-04 | 9 | bar: 2024-03-27 to 2024-04-04
T45 | Schedule D Client - INVESTMENT REVIEWS AND RECOMMENDATIONS | 2024-04-11 | 2024-04-18 | 8 | bar: 2024-04-11 to 2024-04-18
T46 | Schedule A Client - RECOMMENDATIONS MEETING | 2024-04-01 | 2024-04-08 | 8 | bar: 2024-04-01 to 2024-04-08
T47 | Schedule B Client - RECOMMENDATIONS MEETING | 2024-04-08 | 2024-04-15 | 8 | bar: 2024-04-08 to 2024-04-15
T48
C. Documentation and Account Transfers
T49 | Contact LPL M&A Team with notice of P&S | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T50 | Contact LPL M&A Team for Recoding of Non-Advisory Accounts | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T51 | Establish Separate Repcode for all Acquired Comp. | 2024-01-03 | 2024-01-03 | 1 | bar: 2024-01-03
T52 | Prep Advisory Paperwork in ClientWorks | 2024-01-04 | 2024-01-18 | 15 | bar: 2024-01-04 to 2024-01-18
T53 | Queue All Docusigns for required signatures | 2024-01-04 | 2024-01-18 | 15 | bar: 2024-01-04 to 2024-01-18
T54 | Prepare all Paper Mailouts for Signatures | 2024-01-04 | 2024-01-18 | 15 | bar: 2024-01-04 to 2024-01-18
T55 | Confirm Recoding with LPL | 2024-01-06 | 2024-01-06 | 1 | bar: 2024-01-06
T56 | Contact all direct business vendors for re-coding after determining what LPL can do on their side
T57 | New advisor(s) listed on accounts - TPAMs | 2024-01-15 | 2024-02-15 | 32 | bar: 2024-01-15 to 2024-02-15
T58 | New advisor(s) listed on accounts - VAs | 2024-01-15 | 2024-02-15 | 32 | bar: 2024-01-15 to 2024-02-15
T59 | New advisor(s) listed on accounts - MFs | 2024-01-15 | 2024-02-15 | 32 | bar: 2024-01-15 to 2024-02-15
T60 | New advisor(s) listed on accounts - EIAs | 2024-01-15 | 2024-02-15 | 32 | bar: 2024-01-15 to 2024-02-15
Assignment Key -
Corey Wedbush - Lead Entering Advisor
John Smith - Lead Exiting Advisor
Donna Summers - Project Manager
Tom Mix - Marketing/Social Media
Dora Explora - Admin 1 - Prep/Data Entry
Dr. Evil - Admin 2/Process/Data Entry
All Staff
- Move all tasks onto CRM Calendars for advisors and staff once mapped out and agreed to.
- Stay organized!
- Each transition will have different task requirements; modify this spreadsheet for the tasks required for your transition.
- A Smartsheet version of this chart is available through the FRGIS M&A team, the advantage being an online, sole source of recordkeeping.
- Buyers! Use this or a similar plan when presenting to sellers to demonstrate competence in an acquisition.
- Ensure that existing clients are not neglected after the P&S is completed
- (Depending on the size of the practice being acquired), you can count on a good six months of double duty and working hard to pull off an acquisition. It takes work!

## ©
© TemplateLab.com